## Education & Training Work Plan
Training and Education Work Plan
| Category of work |  | Type of resource and/or | Phase Product(s) and/or
|  | Activities | Expertise | Deliverables
I. | Analysis Phase |  | Phase Team Roles*
| 1 | Identify potential need for training (needs assessment) | Analyst | Analysis Tool
| 2 | Conduct root cause analysis | Instructional Designer
| 3 | Identify target audience | Unit Leadership
| 4 | Compile task inventory
| 5 | Select tasks to be performed and taught
| 6 | Determine performance measures for tasks
| 7 | Select desired instructional setting |  | Business Requirements Document
| 8 | Prepare for Design Phase
II. | Design Phase |  | Phase Team Roles*
| 9 | Verify Requirements | Instructional Desiginer
| 10 | Set Course Objectives | Analyst
| 11 | List Observable Behaviors (Pre- and Post-Training) | Subject-Matter Expert
| 12 | Develop Course Topics and Outline
| 13 | Select Instructional Methods |  | Instructional Requirements Document
| 14 | Perform Project Research (e.g., course materials, etc.)
| 15 | Meet with Leadership for "Organizational Readiness"
| 16 | Prepare for Development Phase
III. | Development Phase |  | Phase Team Roles*
| 17 | Conduct Consultations with Subject-Matter Experts | Instructional Desiginer
| 18 | List and Sequence Instructor and Participant Activities | Analyst
| 19 | Develop Course Content Materials (including follow-up activities) | Subject Matter Expert | Course Deliverables (Manuals, Job Aids, etc.) See implementation plan Presentation Template
| 20 | Instructional Design Modifcations | Trainer
| 21 | Course Slides and Instructor Aids | Graphic Designer
| 22 | Develop and Test Student Activities
| 23 | Develop Implementation Plan |  | Implementation Plan
| 24 | Prepare for Implementation Phase
IV. | Implementation Phase |  | Phase Team Roles*
| 25 | Schedule and Contract with Trainer(s) | Training Administrator
| 26 | Trainers' Preparation Time | Analyst
| 27 | Coach Trainers (or conduct Train-the-Trainer) | Quality Assurance
| 28 | Training Session Run-Through (Pilot) | Instructional Designer
| 29 | Modify Course Materials | Unit Leadership
| 30 | Create Course Training Schedule | Support Staff
| 31 | Create and Distribute Course Marketing Materials & Course Marketing | Trainer
| 32 | Particpants Register for Scheduled Courses
| 33 | Print Course Manuals and Rosters
| 34 | Conduct Training Events
| 35 | Prepare Evaluation Materials
| 36 | Prepare for Evaluation Phase
IV. | Evaluation Phase |  | Phase Team Roles*
| 37 | Participants' Course Evaluation | Unit Leadership | Evaluation Template
| 38 | Perform Course Follow-Up Activities | Instructional Designer
| 39 | Unit Evaluation of Course Impact | Trainer | Evaluation Template
| 40 | Perform Course Impact Analysis | Web Administrator | Course Impact Analysis Report
| 41 | Course Modifications (continuous improvement effort) | Graphic Designer
| 42 | Preparation of Course Content for Web Access** |  | Re-purposed materials for web access (if desired)
Course Complete
TOTAL EFFORT
NOTES
*An individual can play more than one role on the phase team; however, more than one person may be necessary for many listed activities.
**Optional (not included in effort estimate)